## Slide 1
From Strategy to Action
Florida FASD State Task Force
Quarterly Meeting – April 23, 2026

## Slide 2
Review of Past 6 Months
Respect Act passed – federal recognition of FASD
Florida landscape work completed – we know the gaps
We have momentum. Now we need to act.

## Slide 3
The Challenge We’re Solving
Original strategic plan was vision-heavy but hard to execute
Too many strategies, not enough owned action steps
We need to focus and simplify so we can actually move forward

## Slide 4
Our New Approach
Rule of 3: 3 priorities at a time
Quarterly sprints instead of multi-year strategies
Every action has an owner, a deadline, and a clear deliverable
Two-layer model: Core Leadership (doers) + Task Force Network (amplifiers)
Yearly Calendar with intentionally focused conversations within the task force

## Slide 5
Two-Layer Model
Core Leadership
Own outcomes
Drive execution
Meet monthly
Task Force Network
Provide connections
Open doors
Complete micro-actions
Meet quarterly
Both layers are essential

## Slide 6
Calendar Going Forward
January
Strategic Plan Micro Goals
April
Strategic Plan Micro Goals
July
FASD Awareness (micro goals to spread awareness)
October
Year in Review (where we are & where to focus)

## Slide 7
Priority 1: Awareness & Professional Education
Annual Outcome: Reach 300+ professionals through FASD education
Q2 Goal: Increase outreach efforts (emails) and new locations
Key Actions:
Create wording to promote
Send out flyer
Outreach to new locations
Determine realistic goals

## Slide 8
Priority 2: Screening (Pilot)
Annual Outcome: Launch 1–2 pilot programs integrating FASD screening
Q2 Goal: Create an Implementation Guide for Home Visitors
Key Actions:
Create implementation guide
Recruit members to participate in 1-time focus group
Review implementation guide

## Slide 9
Priority 3: Policy & Legislative Engagement
Annual Outcome: Engage 3–5 state-level champions for FASD
Q2 Goal: Meet with 2 FL Senators, Identify FASD Champions (1 House / 1 Senate)
Key Actions:
Identify targets
Schedule meetings
Identify champions to assist in the meetings

## Slide 10
How YOU Can Help Today
You don’t need to join a workgroup. You just need to open one door.
Awareness
Who knows a person or organization that might benefit from learning about FASD?
Screening
Who has contacts at Early Steps, child welfare, Healthy Start to join a 1-time focus group?
Policy
Who has a relationship with a legislator or agency leader?

## Slide 11
Micro-Commitments
Make 1 introduction
Send 1 email
Share 1 contact
Attend or support 1 meeting
“Small actions create big momentum”

## Slide 12
Progress Dashboard
Priority Area | Q2 Goal | Status | Lead
Awareness & Professional Education | Increase outreach efforts and new locations |  | 
Screening (Pilot) | Create Implementation Guide for Home Visitors |  | 
Policy & Legislative Engagement | Meet with 2 FL Senators, Identify FASD Champions |  | 
(To be filled in live or after discussion)

## Slide 13
What’s in the Parking Lot (Not This Year)
Statewide FASD conference
Statewide recurring diagnostic clinic funding
Governor’s Council
Public media campaign
These matter – but we’re focusing on what we can accomplish NOW

## Slide 14
What Happens Next
Core leadership meets monthly to drive execution
Full task force meets quarterly to activate network
Progress reported at every meeting – visible and accountable
Non-attendees get follow-up with specific asks

## Slide 16
“Next time we meet, we will report on THESE outcomes and discuss the new goals.”
Thank You
Next Meeting
Thursday, July 23, 2026
9 AM to 10 AM EST